

wbs dictionary



Mohamed Ehab Hassan Sayed

Group 2

Section 3

* 1. Fingerprint devices:

|  |  |
| --- | --- |
| Work package ID | 1.1.1 |
| Work package Name | Getting resources |
| Description | Buying or making the required resources |
| Person(s) | The computer engineers team |
| Start Date | 1/ 1 / 2022 |
| End Date | 31/ 1 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.1.2 |
| Work package Name | Producing the devices |
| Description | Manufacturing the fingerprint-scanning devices |
| Person(s) | The computer engineers team |
| Start Date | 1/ 2 / 2022 |
| End Date | 1/ 4 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.1.3 |
| Work package Name | Software |
| Description | Developing the software to run the devices |
| Person(s) | The developers team |
| Start Date | 1 / 4 / 2022 |
| End Date | 1/ 6 / 2022 |

1.2 Information System:

|  |  |
| --- | --- |
| Work package ID | 1.2.1 |
| Work package Name | Storage system |
| Description | Establishing a reliable storage system |
| Person(s) | The computer engineers team |
| Start Date | 1 / 1 / 2022 |
| End Date | 1 / 3 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.2.2 |
| Work package Name | DBMS |
| Description | Developing a reliable DBMS |
| Person(s) | The developers team |
| Start Date | 1 / 3 / 2022 |
| End Date | 15 / 4 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.2.3 |
| Work package Name | DBMS security |
| Description | Making a strong security system to the DBMS |
| Person(s) | Security admins & The developers team |
| Start Date | 15 / 4 / 2022 |
| End Date | 1 / 6 / 2022 |

1.3 Network:

|  |  |
| --- | --- |
| Work package ID | 1.3.1 |
| Work package Name | Network deployment |
| Description | Connecting the Fingerprint-scanner devices from all around Egypt to the DBMS using a reliable network |
| Person(s) | the network engineers team |
| Start Date | 15 / 4 / 2022 |
| End Date | 1 / 7 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.3.2 |
| Work package Name | Network security |
| Description | Making a strong security system to the Network |
| Person(s) | The security admins team  & Network engineers team |
| Start Date | 1 / 7 / 2022 |
| End Date | 15 / 8 / 2022 |

1.4 Finishing:

|  |  |
| --- | --- |
| Work package ID | 1.4.1 |
| Work package Name | Testing the system |
| Description | Doing some tests to the final system |
| Person(s) | Developers |
| Start Date | 15 / 8 / 2022 |
| End Date | 15 / 9 / 2022 |

|  |  |
| --- | --- |
| Work package ID | 1.4.2 |
| Work package Name | Launching the System |
| Description | Introducing the System to public |
| Person(s) | Manager |
| Start Date | 15 / 9 / 2022 |
| End Date | 1 / 10 / 2022 |

By. Mohamed Ehab Hassan Sayed

Group 2

Section 3